## DIF Checklist 6-14-18
DIF Facilities Documentation Requirements Checklist
Developer:
DIF Category:
DIF Program Project No.:
CFD No.:
Segment No.:
Improvement Construction Period:
Note: City will not begin reviewing submittals until all items on this Checklist are provided.
Date Received From Developer | Binder Tab Reference | DIF Credit and Reimbursement Agreement Reference | CFD Acquisition Agreement Reference | Required Documents | Items to Review | Reviewed By (Egineering/DIF)
|  |  |  | Initiate DIF Credit and Reimbursement Agreement |  | RH Consulting
| A |  |  | Warrant showing $10,000 deposit for DIF Credit and Reimbursement Agreement process |  | Planning
| B |  |  | DIF Credit and Reimbursement Agreement | Approved by City Council and signed by City Manager | DIF
| C |  |  | DIF Agreement Assignment |  | DIF
| D | 2, 16 | 3.3 | DIF Program Facilities Construction Certification form (Though DIF Credit Program does not specify compliance with California Government Code or the California Public Contract Code, these codes are required for acquisitions with CFD bond proceeds.) | Complete and signed | DIF
| E | 2, 16 | 3.3 | Bid document with itemized line item - Developer to highlight and flag each language requirement. | Improvements in accordance with the terms of the individual Tract Maps | DIF
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators to pay at least General Prevailing Wage Rates to all workers employed in the execution of the contract | DIF
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators engaged to perform work on a Segment to submit certified weekly payroll records to the Developer for inspection by the City | DIF
[5 empty] | Require all contractors to register with the California Department of Industrial Relations (DIR) in accordance with SB854 for bids on 1/1/2015 and after | DIF
| F | 2 | 3.3 | Notice Inviting Bids (NIB) | Date of NIB, time and place for the receiving and opening of sealed bid, description of the project, where bid form may be obtained | DIF
| G | 2 | 3.3 | Proof of NIB advertised in newspaper of general circulation such as Daily Bulletin - See different requirement for bid before and after 9/18/2016 | If bid before 8/19/2016, then advertise at least 10 days before the bid due date. If bid on 8/19/2016 and after, then advertise at least 14 days before the bid due date. | DIF
| H | 2 | 3.3 | Proof of NIB sent to all construction trade journals as specified in PCC Section 22036 if bid on 9/18/2016 and after. | If bid on 9/18/2016 and after, then advertise at least 15 days before the bid due date - Construction Bidboard (eBidboard), McGraw-Hill Construction Dodge, Southern California Builders Association, BidAmerica, Associated General Contractors of America | DIF
| I | 2 | 3.3 | Developer written statement describing bidding and awarding process | Award to the responsible bidder submitting the lowest responsive bid | DIF
| J | 2 | 3.3 | Bid tabulation | Award to the responsible bidder submitting the lowest responsive bid | DIF
| K | 16 | 3.3 | Public work contractor registration certification if bid on 3/1/2015 and after | Complete and signed | DIF
| L | 16 | 3.3 | PWC-100 if bid on 6/20/2014 and after | Filed with DIR within 5 days from the award date if bid on 6/20/2014 and after | DIF
| M | 2, 9 | 3.3 | Contracts - Developer to highlight and flag each language requirement to identify the location of each requirement | Copy of all contracts with vendors the DIF Credit Facilities - Summary of Expended and Eligible Costs form is paying for | DIF
[5 empty] | Copy of all contracts with vendors the CFD Segments - Summary of Expended and Eligible Costs form is paying for | DIF
[5 empty] | Prevailing wage rates posted at job-site (Labor Code 1773.2) | DIF
[5 empty] | Workers’ compensation certification (Labor Code 1861) | DIF
[5 empty] | Ineligible contract/subcontractors language (PCC 6109) | DIF
[5 empty] | Apprentice employment language (Labor Code 1777.5) | DIF
[5 empty] | Hours of labor language (Labor Code 1810 & 1811) | DIF
[5 empty] | Penalty for violating hours of labor language (Labor Code 1813) | DIF
[5 empty] | Third-party claims language (PCC 9201) | DIF
[5 empty] | Payroll records (Labor Code 1776(i)) | DIF
[5 empty] | Earthquake and tidal insurance (PCC 7105) | DIF
[5 empty] | Insurance language | DIF
[5 empty] | Contractors’ State license board notice statement (Bus & Prof Code 7030(a) & (b) | DIF
[5 empty] | “Or Equal” provision (PCC 3400) | DIF
[5 empty] | Trenches (Labor Code 6705) | DIF
[5 empty] | Unusual conditions clause (PCC 7104) | DIF
[5 empty] | Utilities (Gov Code 4215) | DIF
[5 empty] | Payment Bond (Civ Code 3247 & 3248) | DIF
[5 empty] | Retention/substitution of security (PCC 22300) | DIF
[5 empty] | Progress payment (PCC 9203(a)) | DIF
[5 empty] | Progress/retention proceeds payment deadline (PCC 7107© & 20104.5(b) | DIF
[5 empty] | Progress payment waiver & release (Civ Code 3262) | DIF
[5 empty] | Claims and dispute resolution (PCC 20104) | DIF
[5 empty] | Anti-trust claim assignment (PCC 7103.5) | DIF
[5 empty] | Stormwater Language (PCC 28026) | DIF
[5 empty] | DIR registration (Labor Code 1771.1(a)) (As of 1/1/2015) | DIF
[5 empty] | Require all contractors, subcontractors, and vendors to pay at least General Prevailing Wage Rates to all workers | DIF
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators engaged to perform work on a Segment to submit certified weekly payroll records to the Developer for inspection by the City | DIF
[5 empty] | Require all contractors, subcontractors, and vendors to comply with the provisions that the contractor shall not discriminate in its employment practices against any employee, or applicant for employment, because of such person’s race, religion, national origin, ancestry, sex, sexual orientation, age, physical handicap, marital status or medical condition. | DIF
| N | 16 | 3.3 | Developer written statement and pictures verifying the General Prevailing Wage Rates were posted at the job-site in a conspicuous place and available to all employees and applicants for employment |  | Engineering
| O | 18 | 3.5, 4.2 | Permits - Developer to list in the space below all the permits required | All permits required by the City or any other government agency affected by the construction of the Improvements (Land Use Entitlement, Encroachment) | Engineering
[5 empty] | Invoice supporting permit fees required | Engineering
[5 empty] | Warrants supporting permit fees paid | Engineering
| P | 3 | 2.2, 3.1 | "As-built" or recorded drawings or plans for the Improvement | Certified and reflecting the condition of the Improvement as constructed in accordance with the Conditions of Approval (COA) | Engineering
| Q | 3 | 3.5 | Acceptance letter from City Engineering Dept |  | Engineering
| R | 3 | 2.2, 3.5 | Copy of NOC filed with San Bernardino County | Filing is within 10-days after receiving notification that the segment was constructed in accordance with the Plans, pursuant to the provisions of Section 3093 of the California Civil Code. | Engineering
| S | 3 | 2.2 | Copy of mechanic's lien | All final releases or documentation that there are no outstanding claims or liens from all contractors, subcontractors, and vendors that received payment as part of the Eligible or Actual Costs or Reimbursement | Engineering
[5 empty] | Guaranteeing that no such claims of liens will be recorded or become a lien upon any of the real property required for the Improvement | Engineering
| T | 3, 4 | 2.2 | Acceptable title | The City Engineer shall review and approve the title report unless it reveals a matter which could materially affect the City’s or its designee’s use and enjoyment of any part of the property or easement covered by the title report. | Engineering
| U | 5 | 3.6 | Maintenance bond (only for subdivision) | Term is one year from the Acceptance Date | Engineering
| V | 3 |  | Binder cover letter from Developer notifying the City Engineer that the construction of a DIF Program Segment has been completed in accordance with the plans and specifications |  | Engineering
| W | 9, Exhibit 6 |  | Form of DIF Credit Request |  | DIF
| X | 6, Exhibit 5 |  | Form of Certificate of Regional or Local Adjacent DIF Credit |  | DIF
| Y | 9, Attachment 1 |  | Summary of Improvements and Requested DIF Credits form |  | DIF
| Z | 10, Exhibit 7 |  | Form of Certificate of DIF Reimbursement |  | DIF
| AA | 6 |  | DIF Credit Facilities - Summary of Expended and Eligible Costs form | Developer identified DIF Credit infrastructure category | Engineer/DIF
[5 empty] | Developer identified whether the DIF Credit is Regional or Local Adjacent DIF Program Improvement | Engineer/DIF
| AB | 7, 8, 12.1, 12.2, 12.3, 12.4 |  | DIF Credit Facilities - Expended and Eligible Costs form | DIF Credit issued by City shall be limited to the amount of the DIF Program Costs for the Improvement accepted | Engineer/DIF
[5 empty] | DIF Program Costs for the Improvements accepted shall be those in effect at the time the Improvement is Completed and accepted by the City | Engineer/DIF
[5 empty] | Total amount of DIF Credit to be issued to Developer for completion of all Improvements shall be limited to the respective DIF Infrastructure Category | Engineer/DIF
[5 empty] | 10% of the DIF Program Costs, for those design costs portion of the Improvements shall be issued to NMC Builders LLC | Engineer/DIF
[5 empty] | Reimbursement amount does not include interest cost | Engineer/DIF
[5 empty] | Reimbursement amount is not for DIF payments made by development that does not benefit from Developer's construction DIF Program Improvements or from DIF payments received for other DIF categories | Engineer/DIF
[5 empty] | In the Regional DIF category of Sewer Collection Facilities, no DIF Reimbursement shall be available from DIF payments until the City's obligations to repay IEUA have been met | Engineer/DIF
[5 empty] | Reimburse in order of the date of certificate issuance | Engineer/DIF
| AC | 9 |  | Change orders |  | Engineer
| AD | 9 |  | Invoices supporting items on the DIF Credit Facilities - Expended and Eligible Costs form - Invoices need to be detailed to show each item. Not lump sum. Traceable from form to invoice. |  | Engineer/DIF
| AE | 9 |  | Warrants supporting items on the DIF Credit Facilities - Expended and Eligible Costs form - Traceable from form to warrant. |  | Engineer/DIF
| AF |  | 1.1, 2.4 | Developer certificate contain an original or specimen signature of each person designated as Developer Representative |  | Engineer/DIF

## DIF Checklist (12-15-2017) (hidden)
DIF Facilities Documentation Requirements Checklist
Developer:
DIF Category:
DIF Program Project No.:
CFD No.:
Segment No.:
Improvement Construction Period:
Note: City will not begin reviewing submittals until all items on this Checklist are provided.
Date Received From Developer | Binder Tab Reference | DIF Reimbursement Agreement Reference | CFD Acquisition Agreement Reference | Required Documents | Items to Review | Reviewed By (Egineering/DIF)
|  |  |  | Initiate DIF Credit and Reimbursement Agreement |  | RH Consulting
| A |  |  | Warrant showing $10,000 deposit for DIF Credit and Reimbursement Agreement process |  | Planning
| B |  |  | DIF Credit and Reimbursement Agreement | Approved by City Council and signed by City Manager | DIF
| C |  |  | DIF Assignment |  | DIF
| D | 2, 16 | 3.3 | DIF Program Facilities Construction Certification form (Though DIF Credit Program does not specify compliance with California Government Code or the California Public Contract Code, these codes are required for acquisitions with CFD bond proceeds.) | Complete and signed | DIF
| E | 2, 16 | 3.3 | Bid document with itemized line item - Developer to highlight and flag each language requirement. | Improvements in accordance with the terms of the individual Tract Maps | DIF
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators to pay at least General Prevailing Wage Rates to all workers employed in the execution of the contract | DIF
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators engaged to perform work on a Segment to submit certified weekly payroll records to the Developer for inspection by the City | DIF
[5 empty] | Require all contractors to register with the California Department of Industrial Relations (DIR) in accordance with SB854 for bids on 1/1/2015 and after | DIF
| F | 2 | 3.3 | Notice Inviting Bids (NIB) | Date of NIB, time and place for the receiving and opening of sealed bid, description of the project, where bid form may be obtained | DIF
| G | 2 | 3.3 | Proof of NIB advertised in Daily Bulletin - See different requirement for bid before and after 9/18/2016 | If bid before 8/19/2016, then advertise at least 10 days before the bid due date. If bid on 8/19/2016 and after, then advertise at least 14 days before the bid due date. | DIF
| H | 2 | 3.3 | Proof of NIB sent to all construction trade journals as specified in PCC Section 22036 if bid on 9/18/2016 and after. | If bid on 9/18/2016 and after, then advertise at least 15 days before the bid due date - Construction Bidboard (eBidboard), McGraw-Hill Construction Dodge, Southern California Builders Association, BidAmerica, Associated General Contractors of America | DIF
| I | 2 | 3.3 | Developer written statement describing bidding and awarding process | Award to the responsible bidder submitting the lowest responsive bid | DIF
| J | 2 | 3.3 | Bid tabulation | Award to the responsible bidder submitting the lowest responsive bid | DIF
| K | 16 | 3.3 | Public work contractor registration certification if bid on 3/1/2015 and after | Complete and signed | DIF
| L | 16 | 3.3 | PWC-100 if bid on 6/20/2014 and after | Filed with DIR within 5 days from the award date if bid on 6/20/2014 and after | DIF
| M | 2, 9 | 3.3 | Contracts - Developer to highlight and flag each language requirement to identify the location of each requirement | Copy of all contracts with vendors the DIF Credit Facilities - Summary of Expended and Eligible Costs form is paying for | DIF
[5 empty] | Copy of all contracts with vendors the CFD Segments - Summary of Expended and Eligible Costs form is paying for | DIF
[5 empty] | Prevailing wage rates posted at job-site (Labor Code 1773.2) | DIF
[5 empty] | Workers’ compensation certification (Labor Code 1861) | DIF
[5 empty] | Ineligible contract/subcontractors language (PCC 6109) | DIF
[5 empty] | Apprentice employment language (Labor Code 1777.5) | DIF
[5 empty] | Hours of labor language (Labor Code 1810 & 1811) | DIF
[5 empty] | Penalty for violating hours of labor language (Labor Code 1813) | DIF
[5 empty] | Third-party claims language (PCC 9201) | DIF
[5 empty] | Payroll records (Labor Code 1776(i)) | DIF
[5 empty] | Earthquake and tidal insurance (PCC 7105) | DIF
[5 empty] | Insurance language | DIF
[5 empty] | Contractors’ State license board notice statement (Bus & Prof Code 7030(a) & (b) | DIF
[5 empty] | “Or Equal” provision (PCC 3400) | DIF
[5 empty] | Trenches (Labor Code 6705) | DIF
[5 empty] | Unusual conditions clause (PCC 7104) | DIF
[5 empty] | Utilities (Gov Code 4215) | DIF
[5 empty] | Payment Bond (Civ Code 3247 & 3248) | DIF
[5 empty] | Retention/substitution of security (PCC 22300) | DIF
[5 empty] | Progress payment (PCC 9203(a)) | DIF
[5 empty] | Progress/retention proceeds payment deadline (PCC 7107© & 20104.5(b) | DIF
[5 empty] | Progress payment waiver & release (Civ Code 3262) | DIF
[5 empty] | Claims and dispute resolution (PCC 20104) | DIF
[5 empty] | Anti-trust claim assignment (PCC 7103.5) | DIF
[5 empty] | Stormwater Language (PCC 28026) | DIF
[5 empty] | DIR registration (Labor Code 1771.1(a)) (As of 1/1/2015) | DIF
[5 empty] | Require all contractors, subcontractors, and vendors to pay at least General Prevailing Wage Rates to all workers | DIF
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators engaged to perform work on a Segment to submit certified weekly payroll records to the Developer for inspection by the City | DIF
[5 empty] | Require all contractors, subcontractors, and vendors to comply with the provisions that the contractor shall not discriminate in its employment practices against any employee, or applicant for employment, because of such person’s race, religion, national origin, ancestry, sex, sexual orientation, age, physical handicap, marital status or medical condition. | DIF
| N | 16 | 3.3 | Developer written statement and pictures verifying the General Prevailing Wage Rates were posted at the job-site in a conspicuous place and available to all employees and applicants for employment |  | Engineering
| O | 18 | 3.5, 4.2 | Permits - Developer to list in the space below all the permits required | All permits required by the City or any other government agency affected by the construction of the Improvements (Land Use Entitlement, Encroachment) | Engineering
[5 empty] | Invoice supporting permit fees required | Engineering
[5 empty] | Warrants supporting permit fees paid | Engineering
| P | 3 | 2.2, 3.1 | "As-built" or recorded drawings or plans for the Improvement | Certified and reflecting the condition of the Improvement as constructed in accordance with the Conditions of Approval (COA) | Engineering
| Q | 3 | 3.5 | Acceptance letter from City Engineering Dept |  | Engineering
| R | 3 | 2.2, 3.5 | Copy of NOC filed with San Bernardino County | Filing is within 10-days after receiving notification that the segment was constructed in accordance with the Plans, pursuant to the provisions of Section 3093 of the California Civil Code. | Engineering
| S | 3 | 2.2 | Copy of mechanic's lien | All final releases or documentation that there are no outstanding claims or liens from all contractors, subcontractors, and vendors that received payment as part of the Eligible or Actual Costs or Reimbursement | Engineering
[5 empty] | Guaranteeing that no such claims of liens will be recorded or become a lien upon any of the real property required for the Improvement | Engineering
| T | 3, 4 | 2.2 | Acceptable title | The City Engineer shall review and approve the title report unless it reveals a matter which could materially affect the City’s or its designee’s use and enjoyment of any part of the property or easement covered by the title report. | Engineering
| U | 5 | 3.6 | Maintenance bond (only for subdivision) | Term is one year from the Acceptance Date | Engineering
| V | 3 |  | Binder cover letter from Developer notifying the City Engineer that the construction of a DIF Program Segment has been completed in accordance with the plans and specifications |  | Engineering
| W | 9, Exhibit 6 |  | Form of DIF Credit Request |  | DIF
| X | 6, Exhibit 5 |  | Form of Certificate of Regional or Local Adjacent DIF Credit |  | DIF
| Y | 9, Attachment 1 |  | Summary of Improvements and Requested DIF Credits form |  | DIF
| Z | 10, Exhibit 7 |  | Form of Certificate of DIF Reimbursement |  | DIF
| AA | 6 |  | DIF Credit Facilities - Summary of DIF Program and Eligible Costs form | Developer identified DIF Credit infrastructure category | Engineer/DIF
[5 empty] | Developer identified whether the DIF Credit is Regional or Local Adjacent DIF Program Improvement | Engineer/DIF
| AB | 7, 8, 12.1, 12.2, 12.3, 12.4 |  | DIF Credit Facilities - Summary of Expended and Eligible Costs form | DIF Credit issued by City shall be limited to the amount of the DIF Program Costs for the Improvement accepted | Engineer/DIF
[5 empty] | DIF Program Costs for the Improvements accepted shall be those in effect at the time the Improvement is Completed and accepted by the City | Engineer/DIF
[5 empty] | Total amount of DIF Credit to be issued to Developer for completion of all Improvements shall be limited to the respective DIF Infrastructure Category | Engineer/DIF
[5 empty] | 10% of the DIF Program Costs, for those design costs portion of the Improvements shall be issued to NMC Builders LLC | Engineer/DIF
[5 empty] | Reimbursement amount does not include interest cost | Engineer/DIF
[5 empty] | Reimbursement amount is not for DIF payments made by development that does not benefit from Developer's construction DIF Program Improvements or from DIF payments received for other DIF categories | Engineer/DIF
[5 empty] | In the Regional DIF category of Sewer Collection Facilities, no DIF Reimbursement shall be available from DIF payments until the City's obligations to repay IEUA have been met | Engineer/DIF
[5 empty] | Reimburse in order of the date of certificate issuance | Engineer/DIF
| AC | 9 |  | Change orders |  | Engineer
| AD | 9 |  | Invoices supporting items on the DIF Credit Facilities - Summary of Expended and Eligible Costs form - Invoices need to be detailed to show each item. Not lump sum. Traceable from form to invoice. |  | Engineer/DIF
| AE | 9 |  | Warrants supporting items on the DIF Credit Facilities - Summary of Expended and Eligible Costs form - Traceable from form to warrant. |  | Engineer/DIF
| AF |  | 1.1, 2.4 | Developer certificate contain an original or specimen signature of each person designated as Developer Representative |  | Engineer/DIF

## DIF Construction Certification
DIF Program Facilities Construction Certification
I hereby certify under penalty of perjury under the laws of the State of California that all of the DIF Program improvements were constructed in compliance with California Labor code, California Government Code, California Public Contracts Code and all of the representations made herein are true and correct for the following facilities/segments:
Signature:
Name:
Title:
Date:

## Summary Eligible Costs 6-14-18
DIF Credit Facilities - Summary of Expended and Eligible Costs
DIF Program Costs
DIF Category | DIF Program Project No. | DIF Program Project Description | Segment Description | Total DIF Program Costs for Segment | DIF Program Construction Costs and Contingency Amount (From DIF Program) | DIF Program - CM Costs (5% of Construction Costs) | DIF Program Costs - Design and CM (15% of Construction Costs)

## Expended Eligible Costs 6-14-18
DIF Credit Facilities - Expended and Eligible Costs
DIF Program Project No. and Description:
Total DIF Program Cost:
List all Contractors, Suppliers, and Vendors
Construction Cost (see Eligible Cost definition in agreement) |  | Final Actual Amount Paid
(Section i) List all Construction Contracts by Name of Contractor/License No.
1.
2.
3.
4.
| Construction Sub-Total | 0
Construction Related Costs (see Eligible Cost definition in agreement) |  | Final Actual Amount Paid
(Section ii) Provide Name of Contractor and Describe Work Performed
1.
2.
3.
4.
| Construction Related Sub-Total | 0
Real Property Costs (see Eligible Cost definition in agreement) |  | Final Actual Amount Paid
(Section iii) Provide Name of Contractor and Describe Work Performed
1.
2.
3.
4.
| Real Property Sub-Total | 0
Bid Document Costs (see Eligible Cost definition in agreement) |  | Final Actual Amount Paid
(Section iv) Provide Name of Contractor and Describe Work Performed
1.
2.
3.
4.
| Bid Document Sub-Total | 0
Fees Costs (see Eligible Cost definition in agreement) |  | Final Actual Amount Paid
(Section v) Provide List of Fees Paid
1.
2.
3.
4.
| Fees Sub-Total | 0
Construction Management Costs (see Eligible Cost definition in agreement) |  | Final Actual Amount Paid
(Section vi) Describe Construction Management Services - List all Service Providers and Amounts
1.
2.
3.
4.
| Construction Management Sub-Total | 0
Professional Services Costs (see Eligible Cost definition in agreement) |  | Final Actual Amount Paid
(Section vii) Provide Name of Contractor and Type of Work Performed
1.
2.
3.
4.
| Professional Services Sub-Total | 0
| Actual Cost Grand Total | 0
| 5% Construction Management Limitation Amount | 0
| 15% Design & Construction Management Limitation Amount | 0
| Total Expended and Eligible Costs | 0
Per DIF Credit and Reimbursement Agreement:
Eligible Cost means the substantiated cost of an Improvement to be used in calculating DIF Credit amounts or DIF Reimbursement amounts, which costs may include:
(i) the costs for the construction (including grading) of such Improvement,
(ii) costs directly related to the construction and/or maintenance bonds, the professional costs of material testing, and insurance costs (including costs of any title insurance required),
(iii) the cost of acquiring any real property or interest therein essential to construct or operate the Improvement,
(iv) the cost incurred in preparing Bid Documents and the related costs of geotechnical and environmental evaluations of the Improvement,
(v) the fees paid to governmental agencies for, and all other costs incurred in connectioin with obraining permits, licenses or other governmental approvals for such Improvement,
(vi) costs of construction and project management, administration and supervision (but only up to five percent (5%) of the costs described in clause (i) above) incurred for the construction of such Improvement,
(vii) professional costs associated with such Improvement, such as engineering, accounting, inspection, construction staking, and similar professional services including legal services related to the review of construction contracts.
The maximum amount of Eligible Costs described in clauses (iv) through (vii) shall be limited to a total of fifteen percent (15%) of the costs described in clause (i).