## CFD Checklist (12-21-2017)
CFD Facilities Documentation Requirements Checklist
Developer:
DIF Category:
DIF Program Project No.:
CFD No.:
Segment No.:
Improvement Construction Period:
Note: City will not begin reviewing submittals until all items on this Checklist are provided.
Date Received From Developer | Binder Tab Reference | DIF Reimbursement Agreement Reference | CFD Acquisition Agreement Reference | Required Documents | Items to Review | Reviewed By (Engineering/CFD)
|  |  |  | Initiate Acquisition Agreement |  | RH Consulting
| A |  |  | Warrant showing $75,000 deposit for Acquisition Agreement |  | CFD
| B |  |  | Acquisition Agreement | Approved by City Council and signed by City Manager | CFD
| C |  |  | DIF Facilities Documentation Requirements Checklist | Verify DIF request has been approved by Engineering and DIF Departments | CFD
| D |  | 3.3 | CFD Program Facilities Construction Certification | Complete and signed | CFD
If Improvements have been approved by Engineering and DIF Departments during DIF review process, skip to Binder Tab Reference V
| E | 2, 16 | 3.3 | Bid document with itemized line item - Developer to highlight and flag each language requirement. | Improvements in accordance with the terms of the individual Tract Maps | CFD
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators to pay at least General Prevailing Wage Rates to all workers employed in the execution of the contract | CFD
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators engaged to perform work on a Segment to submit certified weekly payroll records to the Developer for inspection by the City | CFD
[5 empty] | Require all contractors to register with the California Department of Industrial Relations (DIR) in accordance with SB854 for bids on 1/1/2015 and after | CFD
| F | 2 | 3.3 | Notice Inviting Bids (NIB) | Date of NIB, time and place for the receiving and opening of sealed bid, description of the project, where bid form may be obtained | CFD
| G | 2 | 3.3 | Proof of NIB advertised in a newspaper of general circulation such as Daily Bulletin - See different requirement for bid before and after 9/18/2016 | If bid before 8/19/2016, then advertise at least 10 days before the bid due date. If bid on 8/19/2016 and after, then advertise at least 14 days before the bid due date. | CFD
| H | 2 | 3.3 | Proof of NIB sent to all construction trade journals as specified in PCC Section 22036 if bid on 9/18/2016 and after. | If bid on 9/18/2016 and after, then advertise at least 15 days before the bid due date - Construction Bidboard (eBidboard), McGraw-Hill Construction Dodge, Southern California Builders Association, BidAmerica, Associated General Contractors of America | CFD
| I | 2 | 3.3 | Developer written statement describing bidding and awarding process | Award to the responsible bidder submitting the lowest responsive bid | CFD
| J | 2 | 3.3 | Bid tabulation | Award to the responsible bidder submitting the lowest responsive bid | CFD
| K | 16 | 3.3 | Public work contractor registration certification if bid on 3/1/2015 and after | Complete and signed | CFD
| L | 16 | 3.3 | PWC-100 if bid on 6/20/2014 and after | Filed with DIR within 5 days from the award date if bid on 6/20/2014 and after | CFD
| M | 2, 9 | 3.3 | Contracts - Developer to highlight and flag each language requirement to identify the location of each requirement | Copy of all contracts with vendors the DIF Credit Facilities - Summary of Expended and Eligible Costs (List all Contractors, Suppliers and Vendors) form is paying for | CFD
[5 empty] | Copy of all contracts with vendors the CFD Segments - Summary of Expended and Eligible Costs (List all Contractors, Suppliers and Vendors) form is paying for | CFD
[5 empty] | Prevailing wage rates posted at job-site (Labor Code 1773.2) | CFD
[5 empty] | Workers’ compensation certification (Labor Code 1861) | CFD
[5 empty] | Ineligible contract/subcontractors language (PCC 6109) | CFD
[5 empty] | Apprentice employment language (Labor Code 1777.5) | CFD
[5 empty] | Hours of labor language (Labor Code 1810 & 1811) | CFD
[5 empty] | Penalty for violating hours of labor language (Labor Code 1813) | CFD
[5 empty] | Third-party claims language (PCC 9201) | CFD
[5 empty] | Payroll records (Labor Code 1776(i)) | CFD
[5 empty] | Earthquake and tidal insurance (PCC 7105) | CFD
[5 empty] | Insurance language | CFD
[5 empty] | Contractors’ State license board notice statement (Bus & Prof Code 7030(a) & (b) | CFD
[5 empty] | “Or Equal” provision (PCC 3400) | CFD
[5 empty] | Trenches (Labor Code 6705) | CFD
[5 empty] | Unusual conditions clause (PCC 7104) | CFD
[5 empty] | Utilities (Gov Code 4215) | CFD
[5 empty] | Payment Bond (Civ Code 3247 & 3248) | CFD
[5 empty] | Retention/substitution of security (PCC 22300) | CFD
[5 empty] | Progress payment (PCC 9203(a)) | CFD
[5 empty] | Progress/retention proceeds payment deadline (PCC 7107© & 20104.5(b) | CFD
[5 empty] | Progress payment waiver & release (Civ Code 3262) | CFD
[5 empty] | Claims and dispute resolution (PCC 20104) | CFD
[5 empty] | Anti-trust claim assignment (PCC 7103.5) | CFD
[5 empty] | Stormwater Language (PCC 28026) | CFD
[5 empty] | DIR registration (Labor Code 1771.1(a)) (As of 1/1/2015) | CFD
[5 empty] | Require all contractors, subcontractors, and vendors to pay at least General Prevailing Wage Rates to all workers | CFD
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators engaged to perform work on a Segment to submit certified weekly payroll records to the Developer for inspection by the City | CFD
[5 empty] | Require all contractors, subcontractors, and vendors to comply with the provisions that the contractor shall not discriminate in its employment practices against any employee, or applicant for employment, because of such person’s race, religion, national origin, ancestry, sex, sexual orientation, age, physical handicap, marital status or medical condition. | CFD
| N | 16 | 3.3 | Developer written statement and pictures verifying the General Prevailing Wage Rates were posted at the job-site in a conspicuous place and available to all employees and applicants for employment |  | Engineering
| O | 18 | 3.5, 4.2 | Permits - Developer to list in the space below all the permits required | All permits required by the City or any other government agency affected by the construction of the Improvements (Land Use Entitlement, Encroachment) | Engineering
[5 empty] | Invoice supporting permit fees required | Engineering
[5 empty] | Warrants supporting permit fees paid | Engineering
| P | 3 | 2.2, 3.1 | "As-built" or recorded drawings or plans for the Improvement | Certified and reflecting the condition of the Improvement as constructed in accordance with the Conditions of Approval (COA) | Engineering
| Q | 3 | 3.5 | Acceptance letter from City Engineering Dept |  | Engineering
| R | 3 | 2.2, 3.5 | Copy of NOC filed with San Bernardino County | Filing is within 10-days after receiving notification that the segment was constructed in accordance with the Plans, pursuant to the provisions of Section 3093 of the California Civil Code. | Engineering
| S | 3 | 2.2 | Copy of mechanic's lien | All final releases or documentation that there are no outstanding claims or liens from all contractors, subcontractors, and vendors that received payment as part of the Eligible or Actual Costs or Reimbursement | Engineering
[5 empty] | Guaranteeing that no such claims of liens will be recorded or become a lien upon any of the real property required for the Improvement | Engineering
| T | 3, 4 | 2.2 | Acceptable title | The City Engineer shall review and approve the title report unless it reveals a matter which could materially affect the City’s or its designee’s use and enjoyment of any part of the property or easement covered by the title report. | Engineering
| U | 5 | 3.6 | Maintenance bond (only for subdivision) | Term is one year from the Acceptance Date | Engineering
| V |  | 3.3 | Pre-bid meeting sign-in sheet, if pre-bid meeting is required | Pre-bid meeting occurred at least 5 days after the first advertisement if required. Include time, date, location | CFD
| W |  | 3.3 | Contractor's certification regarding workers' compensation | Complete and signed | CFD
| X |  | 3.3, 3.4 | Bid bond | 10% | CFD
| Y |  | 3.3, 3.4 | Performance bond | 100% | CFD
| Z |  | 3.3 | Payment bond (a.k.a. Security of laborers and materialmen) | 100% | CFD
| AA |  | 3.3 | Non-collusion declaration | Complete and signed | CFD
| AB |  | 3.3 | Subcontractors list | Including name, percentage portion of work, CSLB license number, location of business, DIR registration number if bid occurred on 3/1/2015 and after | CFD
| AC |  | 3.3 | Iran contracting certification | Complete and signed | CFD
| AD |  | 3.3, 3.7 | Insurance certificates - Developer to highlight and flag each requirement | Insurance certificates from each contractor, subcontractor, vendor, equipment operator and owner operator engaged to perform work on a Facilities Segment at all times prior to the final Acceptance Date of all Segments, or Developer may elect to provide the same for the benefit of such contractors, subcontractors, vendors, equipment operators and owner operators | CFD
[5 empty] | All liability insurance policy shall bear an endorsement or shall have attached a rider | CFD
[5 empty] | Protective liability policy - Bodily injury - $1,000,000 each person | CFD
[5 empty] | Protective liability policy - Bodily injury - $2,000,000 each occurrence | CFD
[5 empty] | Protective liability policy - Bodily injury - $1,000,000 each accident for products and completed operations | CFD
[5 empty] | Protective liability policy - Property damage - $1,000,000 each accident | CFD
[5 empty] | Protective liability policy - Workers' compensation - Statutory, with a waiver of subrogation in favor of the City | CFD
[5 empty] | Automobile liability insurance - Automobile bodily injury - $1,000,000 each person | CFD
[5 empty] | Automobile liability insurance - Automobile bodily injury - $2,000,000 each occurrence | CFD
[5 empty] | Automobile liability insurance - Automobile property damage - $1,000,000 each accident | CFD
[5 empty] | Include the following statement shall be included on the insurance certificate: “Additional Insured: The insurer agrees that the City, its City Council, and/or all City Council appointed groups, committees, boards and any other City Council appointed body, and/or elective and appointive officers, servants, agents or employees of the City, when acting as such, are additional insureds hereunder, for the acts of the insured, and such insurance shall be primary to any insurance of the City.” | CFD
| AE |  | 3.5 | Binder cover letter from Developer notifying City Engineering Dept of completion of a Facilities Segment | Insure work of construction is accomplished in accordance with the Plans | Engineering
| AF |  | 2.2, 4.2, Exhibit B | Form of Payment Request | City Engineer review to confirm that segment is complete and constructed accordance with the plans and specifications | Engineer/CFD
[5 empty] | For Circulatory System Segments, if substantially complete, then need to submit one payment request for substantially complete and then another payment request when it is 100% complete. | Engineer/CFD
| AG |  | 2.2, Exhibit B | Confirmation and Approval by the City Engineer form | Identify which paragraph to use for City Engineer to sign | Engineer
| AH |  | 2.2, Exhibit B - Attachement A | Segment, Acquisition Cost, Actual Cost, Purchase Price form |  | Engineer/CFD
| AI |  | 2.1, 2.2, Exhibit B - Attachment B | Purchase Price Payment Instructions form | Paid from Net Proceeds of Special Taxes and Net Proceeds of Bonds deposited in the Improvement Fund | CFD
[5 empty] | Net Proceeds of the Special Taxes and Bonds shall be applied to the uses in the priorities set forth in the Memorandum of Agreement | CFD
[5 empty] | If amounts remain in the Improvement Fund after all Acquisition Costs have been paid, deposite in the NMC Acquisition Fund | CFD
| AJ |  | 2.2 | CFD Acquisition Agreement Facilities – Summary of Actual and Eligible Costs form |  | Engineer/CFD
| AK |  | 2.2 | CFD Segments – Summary of Expended and Eligible Costs form | If the City Engineer determines that the Actual Cost specified in such Payment Request as initially submitted exceeds the Developer’s actual, reasonable cost of constructing the Facilities Segment, the Developer shall resubmit the Payment Request, with the Actual Cost specified therein modified so as to take into account such determination by the City Engineer | Engineer/CFD
[5 empty] | Upon confirmation that such Segment is Complete and has been constructed in accordance with the plans and specifications and the City Engineer has verified and approved of the Actual Cost of such Segment, the City Engineer shall sign the Payment Request and forward the approved Pay Request to the Administrative Services Department | Engineer/CFD
| AL |  | 2.2 | Invoices supporting items on the CFD Segments - Summary of Expended and Eligible Costs form - Invoices need to be detailed to show each item. Not lump sum. |  | Engineer/CFD
| AM |  | 2.2 | Warrants supporting items on the CFD Segmetns - Summary of Expended and Eligible Costs form |  | Engineer/CFD
| AN |  | 2.4 | Developer written request for payments of credit amounts (over/under payments) including amount to be paid and amount | Signed by Developer Representative on the Developer certificate containing an original or specimen signature | CFD
| AO |  | 2.4 | Developer calculation demonstrating the amount of credit amount (over/under payments) |  | CFD
| AP |  | 1.1, 2.4 | Developer certificate contain an original or specimen signature of each person designated as Developer Representative |  | CFD

## CFD Checklist (12-15-2017) (hidden)
CFD Facilities Documentation Requirements Checklist
Developer:
DIF Category:
DIF Program Project No.:
CFD No.:
Segment No.:
Improvement Construction Period:
Note: City will not begin reviewing submittals until all items on this Checklist are provided.
Date Received From Developer | Binder Tab Reference | DIF Reimbursement Agreement Reference | CFD Acquisition Agreement Reference | Required Documents | Items to Review | Reviewed By (Egineering/CFD)
|  |  |  | Initiate Acquisition Agreement |  | RH Consulting
| A |  |  | Warrant showing $75,000 deposit for Acquisition Agreement |  | CFD
| B |  |  | Acquisition Agreement | Approved by City Council and signed by City Manager | CFD
| C |  |  | DIF Facilities Documentation Requirements Checklist | Verify DIF request has been approved by Engineering and DIF Departments | CFD
| D |  | 3.3 | CFD Program Facilities Construction Certification | Complete and signed | CFD
If Improvements have been approved by Engineering and DIF Departments during DIF review process, skip to Binder Tab Reference V
| E | 2, 16 | 3.3 | Bid document with itemized line item - Developer to highlight and flag each language requirement. | Improvements in accordance with the terms of the individual Tract Maps | CFD
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators to pay at least General Prevailing Wage Rates to all workers employed in the execution of the contract | CFD
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators engaged to perform work on a Segment to submit certified weekly payroll records to the Developer for inspection by the City | CFD
[5 empty] | Require all contractors to register with the California Department of Industrial Relations (DIR) in accordance with SB854 for bids on 1/1/2015 and after | CFD
| F | 2 | 3.3 | Notice Inviting Bids (NIB) | Date of NIB, time and place for the receiving and opening of sealed bid, description of the project, where bid form may be obtained | CFD
| G | 2 | 3.3 | Proof of NIB advertised in Daily Bulletin - See different requirement for bid before and after 9/18/2016 | If bid before 8/19/2016, then advertise at least 10 days before the bid due date. If bid on 8/19/2016 and after, then advertise at least 14 days before the bid due date. | CFD
| H | 2 | 3.3 | Proof of NIB sent to all construction trade journals as specified in PCC Section 22036 if bid on 9/18/2016 and after. | If bid on 9/18/2016 and after, then advertise at least 15 days before the bid due date - Construction Bidboard (eBidboard), McGraw-Hill Construction Dodge, Southern California Builders Association, BidAmerica, Associated General Contractors of America | CFD
| I | 2 | 3.3 | Developer written statement describing bidding and awarding process | Award to the responsible bidder submitting the lowest responsive bid | CFD
| J | 2 | 3.3 | Bid tabulation | Award to the responsible bidder submitting the lowest responsive bid | CFD
| K | 16 | 3.3 | Public work contractor registration certification if bid on 3/1/2015 and after | Complete and signed | CFD
| L | 16 | 3.3 | PWC-100 if bid on 6/20/2014 and after | Filed with DIR within 5 days from the award date if bid on 6/20/2014 and after | CFD
| M | 2, 9 | 3.3 | Contracts - Developer to highlight and flag each language requirement to identify the location of each requirement | Copy of all contracts with vendors the DIF Credit Facilities - Summary of Expended and Eligible Costs (List all Contractors, Suppliers and Vendors) form is paying for | CFD
[5 empty] | Copy of all contracts with vendors the CFD Segments - Summary of Expended and Eligible Costs (List all Contractors, Suppliers and Vendors) form is paying for | CFD
[5 empty] | Prevailing wage rates posted at job-site (Labor Code 1773.2) | CFD
[5 empty] | Workers’ compensation certification (Labor Code 1861) | CFD
[5 empty] | Ineligible contract/subcontractors language (PCC 6109) | CFD
[5 empty] | Apprentice employment language (Labor Code 1777.5) | CFD
[5 empty] | Hours of labor language (Labor Code 1810 & 1811) | CFD
[5 empty] | Penalty for violating hours of labor language (Labor Code 1813) | CFD
[5 empty] | Third-party claims language (PCC 9201) | CFD
[5 empty] | Payroll records (Labor Code 1776(i)) | CFD
[5 empty] | Earthquake and tidal insurance (PCC 7105) | CFD
[5 empty] | Insurance language | CFD
[5 empty] | Contractors’ State license board notice statement (Bus & Prof Code 7030(a) & (b) | CFD
[5 empty] | “Or Equal” provision (PCC 3400) | CFD
[5 empty] | Trenches (Labor Code 6705) | CFD
[5 empty] | Unusual conditions clause (PCC 7104) | CFD
[5 empty] | Utilities (Gov Code 4215) | CFD
[5 empty] | Payment Bond (Civ Code 3247 & 3248) | CFD
[5 empty] | Retention/substitution of security (PCC 22300) | CFD
[5 empty] | Progress payment (PCC 9203(a)) | CFD
[5 empty] | Progress/retention proceeds payment deadline (PCC 7107© & 20104.5(b) | CFD
[5 empty] | Progress payment waiver & release (Civ Code 3262) | CFD
[5 empty] | Claims and dispute resolution (PCC 20104) | CFD
[5 empty] | Anti-trust claim assignment (PCC 7103.5) | CFD
[5 empty] | Stormwater Language (PCC 28026) | CFD
[5 empty] | DIR registration (Labor Code 1771.1(a)) (As of 1/1/2015) | CFD
[5 empty] | Require all contractors, subcontractors, and vendors to pay at least General Prevailing Wage Rates to all workers | CFD
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators engaged to perform work on a Segment to submit certified weekly payroll records to the Developer for inspection by the City | CFD
[5 empty] | Require all contractors, subcontractors, and vendors to comply with the provisions that the contractor shall not discriminate in its employment practices against any employee, or applicant for employment, because of such person’s race, religion, national origin, ancestry, sex, sexual orientation, age, physical handicap, marital status or medical condition. | CFD
| N | 16 | 3.3 | Developer written statement and pictures verifying the General Prevailing Wage Rates were posted at the job-site in a conspicuous place and available to all employees and applicants for employment |  | Engineering
| O | 18 | 3.5, 4.2 | Permits - Developer to list in the space below all the permits required | All permits required by the City or any other government agency affected by the construction of the Improvements (Land Use Entitlement, Encroachment) | Engineering
[5 empty] | Invoice supporting permit fees required | Engineering
[5 empty] | Warrants supporting permit fees paid | Engineering
| P | 3 | 2.2, 3.1 | "As-built" or recorded drawings or plans for the Improvement | Certified and reflecting the condition of the Improvement as constructed in accordance with the Conditions of Approval (COA) | Engineering
| Q | 3 | 3.5 | Acceptance letter from City Engineering Dept |  | Engineering
| R | 3 | 2.2, 3.5 | Copy of NOC filed with San Bernardino County | Filing is within 10-days after receiving notification that the segment was constructed in accordance with the Plans, pursuant to the provisions of Section 3093 of the California Civil Code. | Engineering
| S | 3 | 2.2 | Copy of mechanic's lien | All final releases or documentation that there are no outstanding claims or liens from all contractors, subcontractors, and vendors that received payment as part of the Eligible or Actual Costs or Reimbursement | Engineering
[5 empty] | Guaranteeing that no such claims of liens will be recorded or become a lien upon any of the real property required for the Improvement | Engineering
| T | 3, 4 | 2.2 | Acceptable title | The City Engineer shall review and approve the title report unless it reveals a matter which could materially affect the City’s or its designee’s use and enjoyment of any part of the property or easement covered by the title report. | Engineering
| U | 5 | 3.6 | Maintenance bond (only for subdivision) | Term is one year from the Acceptance Date | Engineering
| V |  | 3.3 | Pre-bid meeting sign-in sheet, if pre-bid meeting is required | Pre-bid meeting occurred at least 5 days after the first advertisement if required. Include time, date, location | CFD
| W |  | 3.3 | Contractor's certification regarding workers' compensation | Complete and signed | CFD
| X |  | 3.3, 3.4 | Bid bond | 10% | CFD
| Y |  | 3.3, 3.4 | Performance bond | 100% | CFD
| Z |  | 3.3 | Payment bond (a.k.a. Security of laborers and materialmen) | 100% | CFD
| AA |  | 3.3 | Non-collusion declaration | Complete and signed | CFD
| AB |  | 3.3 | Subcontractors list | Including name, percentage portion of work, CSLB license number, location of business, DIR registration number if bid occurred on 3/1/2015 and after | CFD
| AC |  | 3.3 | Iran contracting certification | Complete and signed | CFD
| AD |  | 3.3, 3.7 | Insurance certificates - Developer to highlight and flag each requirement | Insurance certificates from each contractor, subcontractor, vendor, equipment operator and owner operator engaged to perform work on a Facilities Segment at all times prior to the final Acceptance Date of all Segments, or Developer may elect to provide the same for the benefit of such contractors, subcontractors, vendors, equipment operators and owner operators | CFD
[5 empty] | All liability insurance policy shall bear an endorsement or shall have attached a rider | CFD
[5 empty] | Protective liability policy - Bodily injury - $1,000,000 each person | CFD
[5 empty] | Protective liability policy - Bodily injury - $2,000,000 each occurrence | CFD
[5 empty] | Protective liability policy - Bodily injury - $1,000,000 each accident for products and completed operations | CFD
[5 empty] | Protective liability policy - Property damage - $1,000,000 each accident | CFD
[5 empty] | Protective liability policy - Workers' compensation - Statutory, with a waiver of subrogation in favor of the City | CFD
[5 empty] | Automobile liability insurance - Automobile bodily injury - $1,000,000 each person | CFD
[5 empty] | Automobile liability insurance - Automobile bodily injury - $2,000,000 each occurrence | CFD
[5 empty] | Automobile liability insurance - Automobile property damage - $1,000,000 each accident | CFD
[5 empty] | Include the following statement shall be included on the insurance certificate: “Additional Insured: The insurer agrees that the City, its City Council, and/or all City Council appointed groups, committees, boards and any other City Council appointed body, and/or elective and appointive officers, servants, agents or employees of the City, when acting as such, are additional insureds hereunder, for the acts of the insured, and such insurance shall be primary to any insurance of the City.” | CFD
| AE |  | 3.5 | Binder cover letter from Developer notifying City Engineering Dept of completion of a Facilities Segment | Insure work of construction is accomplished in accordance with the Plans | Engineering
| AF |  | 2.2, 4.2, Exhibit B | Form of Payment Request | City Engineer review to confirm that segment is complete and constructed accordance with the plans and specifications | Engineer/CFD
[5 empty] | For Circulatory System Segments, if substantially complete, then need to submit one payment request for substantially complete and then another payment request when it is 100% complete. | Engineer/CFD
| AG |  | 2.2, Exhibit B | Confirmation and Approval by the City Engineer form | Identify which paragraph to use for City Engineer to sign | Engineer
| AH |  | 2.2, Exhibit B - Attachement A | Segment, Acquisition Cost, Actual Cost, Purchase Price form |  | Engineer/CFD
| AI |  | 2.1, 2.2, Exhibit B - Attachment B | Purchase Price Payment Instructions form | Paid from Net Proceeds of Special Taxes and Net Proceeds of Bonds deposited in the Improvement Fund | CFD
[5 empty] | Net Proceeds of the Special Taxes and Bonds shall be applied to the uses in the priorities set forth in the Memorandum of Agreement | CFD
[5 empty] | If amounts remain in the Improvement Fund after all Acquisition Costs have been paid, deposite in the NMC Acquisition Fund | CFD
| AJ |  | 2.2 | CFD Acquisition Agreement Facilities – Summary of Actual and Eligible Costs form |  | Engineer/CFD
| AK |  | 2.2 | CFD Segments – Summary of Expended and Eligible Costs form | If the City Engineer determines that the Actual Cost specified in such Payment Request as initially submitted exceeds the Developer’s actual, reasonable cost of constructing the Facilities Segment, the Developer shall resubmit the Payment Request, with the Actual Cost specified therein modified so as to take into account such determination by the City Engineer | Engineer/CFD
[5 empty] | Upon confirmation that such Segment is Complete and has been constructed in accordance with the plans and specifications and the City Engineer has verified and approved of the Actual Cost of such Segment, the City Engineer shall sign the Payment Request and forward the approved Pay Request to the Administrative Services Department | Engineer/CFD
| AL |  | 2.2 | Invoices supporting items on the CFD Segments - Summary of Expended and Eligible Costs form - Invoices need to be detailed to show each item. Not lump sum. |  | Engineer/CFD
| AM |  | 2.2 | Warrants supporting items on the CFD Segmetns - Summary of Expended and Eligible Costs form |  | Engineer/CFD
| AN |  | 2.4 | Developer written request for payments of credit amounts (over/under payments) including amount to be paid and amount | Signed by Developer Representative on the Developer certificate containing an original or specimen signature | CFD
| AO |  | 2.4 | Developer calculation demonstrating the amount of credit amount (over/under payments) |  | CFD
| AP |  | 1.1, 2.4 | Developer certificate contain an original or specimen signature of each person designated as Developer Representative |  | CFD

## Actual Cost Definition
Actual Cost Definition
“Actual Cost” means, with respect to a Segment, an amount equal to the sum of (a) the Developer’s actual, reasonable cost of constructing such Segment (including grading for such construction), including labor, material and equipment costs, (b) the Developer’s actual, reasonable cost of designing and preparing the Plans for such Segment, including engineering services provided in connection with designing and preparing such Plans, (c) the Developer’s actual, reasonable cost of any performance and maintenance bonds and insurance, including title insurance, required hereby for such Segment, (d) the Developer’s actual, reasonable cost of any real property or interest therein, other than any such real property or interest therein to be conveyed with a Circulation System Segment, which real property or interest therein is either necessary for the construction of such Segment (e.g., temporary construction easements, haul roads, etc.) or is required to be conveyed with such Segment in order to convey Acceptable Title thereto to the City or its designee, (e) the Developer’s actual, reasonable cost of environmental evaluations required in the City’s reasonable determination specifically for such Segment, (f) the amount of any fees actually paid by the Developer to governmental agencies in order to obtain permits, licenses or other necessary governmental approvals and reviews for such Segment, including the City plan check, processing and inspection fees for such Segment, (g) the Developer’s actual, reasonable cost for construction management services for such Segment, which cost shall not exceed 5% of the cost of constructing such Segment, as determined pursuant to clause (a) of this definition, and (h) the Developer’s actual, reasonable cost for professional services directly related to the construction of such Segment, including engineering, inspection, construction staking, materials testing and similar professional services, all as specified in a Payment Request that has been reviewed and approved by the City Engineer; provided, however, that (i) no item of cost relating to a Segment shall be included in more than one category of cost specified in clauses (a) through (h) of this definition, (ii) except with respect to items of cost for construction management services specified in clause (g) that are provided by the Developer or an Affiliate thereof rather than a third party, each item of cost shall include only amounts actually paid by the Developer to third parties, other than Affiliates of the Developer, and shall not include overhead or other internal expenses of the Developer, and (iii) the aggregate cost of items specified in clauses (e) through (h) shall not exceed 15% of the cost of constructing such Segment, as determined pursuant to clause (a) of this definition.

## CFD Construction Certification
CFD Program Facilities Construction Certification
I hereby certify under penalty of perjury under the laws of the State of California that all of the CFD Program improvements were constructed in compliance with California Labor code, California Government Code, California Public Contracts Code and all of the representations made herein are true and correct for the following facilities/segments:
Signature:
Name:
Title:
Date:

## Actual Eligible Costs
CFD Acquisition Agreement Facilities - Summary of Actual and Eligible Costs
Actual Costs
DIF Category | Acquisition Agreement Facilities Segment No. | DIF Program Project No. | Acquisition Agreement Component Description | Acquisition Agreement Segment Description | Total Acquisition Costs for Segment (From Acquisition Agreement) | Actual Construction Costs - See Cost Item (a) | CM Costs limitation (5% of Actual Construction Costs) | Professional Services Cost limitation (15% of Actual Construction Costs)

## Expended Eligible Costs
CFD Segments - Summary of Expended and Eligible Costs
List all Contractors, Suppliers and Vendors
Costs of Construction - Actual Cost Item (a) | Final Actual Amount Paid
(List all Construction Contracts by Name of Contractor/License No.)
Construction Total - Costs Item (a) Total | 0
Preparation of Plans and Engineering Services - Actual Costs Item (b) | Final Actual Amount Paid
Provide Name of Service Provider and Describe Work Performed
Section (b) Total | 0
Performance and Maintenance Bonds - Actual Costs Item (c) | Final Actual Amount Paid
Provide Name of Service Provider and Bond
Section (c) Total | 0
Real Property Costs - Actual Costs Item (d) | Final Actual Amount Paid
Provide Name of Payee
Section (d) Total | 0
Environmental Evaluations -Actual Costs Item (e) | Final Actual Amount Paid
Provide Name of Service Provider and Describe Service
Section (e) Total | 0
Governmental Fees - Actual Costs Item (f) | Final Actual Amount Paid
Provide Name of Agency and Type of Fee or Permit
Section (f) Total | 0
Construction Management, Administration and Supervison - Actual Costs Item (g) | Final Actual Amount Paid
Describe Construction Management Services - List all Service Providers and Amounts
Section (g) Total | 0
Other Professional Services - Actual Costs Item (h) | Final Actual Amount Paid
Describe all other Professional services, including engineering, inspection, construction staking, materials testing and similar professional services
Section (h) Total | 0
Calculate 5% CM Limitation Amount (5% of (a) above) | 0
Calculate 15% Total Professional Services Limitation Amount (15% of Cost Items (e) through (h), above) | 0
Total Expended and Eligible Costs | 0

## Credit Amount Calc (7-5-2018)
CFD # _____ CREDIT AMOUNT CALCULATION
(Acquisition Agreement Section 2.4)
Segment No. | Program Budget | Acutal Costs | (Under) Program Costs | Over Program Costs
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
Totals | 0 | 0 | 0 | 0
|  |  | Eligible Credit Amount = | 0