## DIF & CFD Checklist (v 101019)
DIF & CFD Facilities Documentation Requirements Checklist
Developer Name: | [7 empty] | DIF Program Project No.:
DIF Category: | [7 empty] | DIF Approval Status:
CFD District No.:
CFD Segment No.:
Improvement Construction Period:
Note: City will not begin reviewing submittals until all items on this Checklist have been provided.
Date Received From Developer | Binder Tab Reference Before | Binder Tab Reference | DIF Credit and Reimbursement Agreement Reference | CFD Acquisition Agreement Reference | DIF or CFD Requirements | Required Documents | Items to Review by City | Reviewed By | Comments (Items without documents, including N/A items, must insert a written explanation in the Tab)
| V | A | 2 | 3.5 | Both | Binder cover letter from Developer notifying the City Engineer that the construction of a Segment has been completed in accordance with the plans and specifications | Insure work of construction is accomplished in accordance with the plans and specifications | Development Admin
| B | B |  |  | Both | DIF Credit and Reimbursement Agreement or Acquisition Agreement | Verify this is done and approved by City Council and signed by City Manager | Development Admin
| C | C | 13, Exhibit 8 |  | DIF | DIF Agreement Assignment notification (This applies if you are the assignee.) | Verify this is done, if applicable | Development Admin
| AF | D |  | 1.1, 2.4 | Both | Developer certificate contain an original or specimen signature of each person designated as Developer Representative | Sigature on request matches the designated person on the Developer certificate. Not Applicable - if signature is same as signature on executed agreement. | Finance
| W | E | 9, Exhibit 6 |  | DIF | Form of DIF Credit Request | Sigature on request matches the designated person on the Developer certificate | Finance
| Y | F | 9, Attachment 1 | Attachment 1 | DIF | Summary of Improvements and Requested DIF Credits form | Completeness and accurate reflection of request | Finance
| X | G | 6, 10 Exhibit 5, 7 |  | DIF | Form of Certificate of Regional or Local Adjacent DIF Credit or Form of Certificate of DIF Reimbursement if this is a reimbursement request | Completeness and accurate reflection of request before requesting for City Manager's signature approval | Finance
| AF | H |  | 2.2, 2.3, 4.2, Exhibit B | CFD | Form of Payment Request. | Sigature on request matches the designated person on the Developer certificate. | Finance
[7 empty] | For Circulatory System Segments, if substantially complete, then need to submit one payment request for substantially complete and then another payment request when it is 100% complete. | Finance
| AG | I |  | 2.2, Exhibit B | CFD | Confirmation and Approval by the City Engineer form. Developer to submit this form with appropriate paragraph from the form. | Accurate reflection of request | Engineer & Finance
|  | J |  | 2.2, Exhibit B - Attachement A | CFD | Segment, Acquisition Cost, Actual Cost, Purchase Price form | Completeness and accurate reflection of request | Finance
|  | K |  | 2.1, 2.2, Exhibit B - Attachment B | CFD | Purchase Price Payment Instructions form | Completeness and accurate reflection of request | Finance
| AA | L | 6 | 2.2 | Both | Summary of Expended and Eligible Costs form (Copy of all contracts with vendors listed on the form must be submitted) | Completeness and accurate reflection of request | Engineer & Finance
| AB | M | 7, 8, 12 | 2.2 | DIF | Summary of Actual and Eligible Costs form | DIF Credit issued by City shall be limited to the amount of the DIF Program Costs for the Improvement accepted | Engineer & Finance
|  | N | 2, 16 | 3.3 | CFD | Facilities Construction Certification form (Though DIF Credit Program does not specify compliance with California Government Code or the California Public Contract Code, these codes are required for acquisitions with CFD bond proceeds.) | Complete and signed | Finance
|  | O |  |  | Both | DIF/CFD Facilities Requirements/Supporting Documention Exhibit A Form | Complete and signed | Finance
|  | P | 9 |  | Both | Contracts and Change Orders | Reasonable and accurate reflection of request | Engineer
| AD | Q | 9 | 2.2 | Both | Invoices on the Expended and Eligible Costs form - Invoices need to be detailed to show each item. Not lump sum. Traceable from form to invoice. Please place respective invoices behind each warrant/check. Cancelled checks or other documentation as determined by the City shall be required if Unconditional Waiver Release Forms are not submitted. | Reasonable and accurate reflection of request | Engineer
| AN | R |  | 2.4 | CFD | Developer written request for payments of credit amounts (over/under payments) including amount to be paid, if applicable. | Signed by Developer Representative on the Developer certificate containing an original or specimen signature | Finance
| AO |  |  |  |  | Developer calculation demonstrating the amount of credit amount (over/under payments), if applicable | Completeness and accurate reflection of request | Finance
| O | S | 18 | 4.2 | Both | Permits | All permits required by the City or any other government agency affected by the construction of the Improvements (Land Use Entitlement, Encroachment) | Engineering
| P | T | 3 | 2.2, 3.1 | Both | Record drawings (required for CFD) or approved plans (requried for DIF) for the Improvements signed by City Engineer | Certified and reflecting the condition of the Improvement as constructed in accordance with the Conditions of Approval (COA) | Engineering
| R | U | 3 | 2.2, 3.5 | Both | Copy of NOC filed with San Bernardino County | Filing is within 10-days after receiving notification that the segment was constructed in accordance with the Plans, pursuant to the provisions of Section 3093 of the California Civil Code. | Engineering
| S | V | 3 | 2.2 | Both | Unconditional Waiver Release Forms | All final releases or documentation that there are no outstanding claims or liens from all contractors, subcontractors, and vendors that received payment as part of the Eligible or Actual Costs or Reimbursement | Engineering
[7 empty] | Guaranteeing that no such claims of liens will be recorded or become a lien upon any of the real property required for the Improvement | Engineering
[7 empty] | If applicable, the City Engineer shall review and approve the title report unless it reveals a matter which could materially affect the City’s or its designee’s use and enjoyment of any part of the property or easement covered by the title report. | Engineering
|  | W |  | 3.5 | CFD | Off-site Improvements Aceptance Letter Signed by the City Engineer |  | Engineering
|  | X |  | 3.6 | CFD | Warranty Bond | Term is one year from the Aceptance Date | Engineering

## DIF Checklist (12-15-2017) (hidden)
DIF Facilities Documentation Requirements Checklist
Developer:
DIF Category:
DIF Program Project No.:
CFD No.:
Segment No.:
Improvement Construction Period:
Note: City will not begin reviewing submittals until all items on this Checklist are provided.
Date Received From Developer | Binder Tab Reference | DIF Reimbursement Agreement Reference | CFD Acquisition Agreement Reference | Required Documents | Items to Review | Reviewed By (Egineering/DIF)
|  |  |  | Initiate DIF Credit and Reimbursement Agreement |  | RH Consulting
| A |  |  | Warrant showing $10,000 deposit for DIF Credit and Reimbursement Agreement process |  | Planning
| B |  |  | DIF Credit and Reimbursement Agreement | Approved by City Council and signed by City Manager | DIF
| C |  |  | DIF Assignment |  | DIF
| D | 2, 16 | 3.3 | DIF Program Facilities Construction Certification form (Though DIF Credit Program does not specify compliance with California Government Code or the California Public Contract Code, these codes are required for acquisitions with CFD bond proceeds.) | Complete and signed | DIF
| E | 2, 16 | 3.3 | Bid document with itemized line item - Developer to highlight and flag each language requirement. | Improvements in accordance with the terms of the individual Tract Maps | DIF
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators to pay at least General Prevailing Wage Rates to all workers employed in the execution of the contract | DIF
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators engaged to perform work on a Segment to submit certified weekly payroll records to the Developer for inspection by the City | DIF
[5 empty] | Require all contractors to register with the California Department of Industrial Relations (DIR) in accordance with SB854 for bids on 1/1/2015 and after | DIF
| F | 2 | 3.3 | Notice Inviting Bids (NIB) | Date of NIB, time and place for the receiving and opening of sealed bid, description of the project, where bid form may be obtained | DIF
| G | 2 | 3.3 | Proof of NIB advertised in Daily Bulletin - See different requirement for bid before and after 9/18/2016 | If bid before 8/19/2016, then advertise at least 10 days before the bid due date. If bid on 8/19/2016 and after, then advertise at least 14 days before the bid due date. | DIF
| H | 2 | 3.3 | Proof of NIB sent to all construction trade journals as specified in PCC Section 22036 if bid on 9/18/2016 and after. | If bid on 9/18/2016 and after, then advertise at least 15 days before the bid due date - Construction Bidboard (eBidboard), McGraw-Hill Construction Dodge, Southern California Builders Association, BidAmerica, Associated General Contractors of America | DIF
| I | 2 | 3.3 | Developer written statement describing bidding and awarding process | Award to the responsible bidder submitting the lowest responsive bid | DIF
| J | 2 | 3.3 | Bid tabulation | Award to the responsible bidder submitting the lowest responsive bid | DIF
| K | 16 | 3.3 | Public work contractor registration certification if bid on 3/1/2015 and after | Complete and signed | DIF
| L | 16 | 3.3 | PWC-100 if bid on 6/20/2014 and after | Filed with DIR within 5 days from the award date if bid on 6/20/2014 and after | DIF
| M | 2, 9 | 3.3 | Contracts - Developer to highlight and flag each language requirement to identify the location of each requirement | Copy of all contracts with vendors the DIF Credit Facilities - Summary of Expended and Eligible Costs form is paying for | DIF
[5 empty] | Copy of all contracts with vendors the CFD Segments - Summary of Expended and Eligible Costs form is paying for | DIF
[5 empty] | Prevailing wage rates posted at job-site (Labor Code 1773.2) | DIF
[5 empty] | Workers’ compensation certification (Labor Code 1861) | DIF
[5 empty] | Ineligible contract/subcontractors language (PCC 6109) | DIF
[5 empty] | Apprentice employment language (Labor Code 1777.5) | DIF
[5 empty] | Hours of labor language (Labor Code 1810 & 1811) | DIF
[5 empty] | Penalty for violating hours of labor language (Labor Code 1813) | DIF
[5 empty] | Third-party claims language (PCC 9201) | DIF
[5 empty] | Payroll records (Labor Code 1776(i)) | DIF
[5 empty] | Earthquake and tidal insurance (PCC 7105) | DIF
[5 empty] | Insurance language | DIF
[5 empty] | Contractors’ State license board notice statement (Bus & Prof Code 7030(a) & (b) | DIF
[5 empty] | “Or Equal” provision (PCC 3400) | DIF
[5 empty] | Trenches (Labor Code 6705) | DIF
[5 empty] | Unusual conditions clause (PCC 7104) | DIF
[5 empty] | Utilities (Gov Code 4215) | DIF
[5 empty] | Payment Bond (Civ Code 3247 & 3248) | DIF
[5 empty] | Retention/substitution of security (PCC 22300) | DIF
[5 empty] | Progress payment (PCC 9203(a)) | DIF
[5 empty] | Progress/retention proceeds payment deadline (PCC 7107© & 20104.5(b) | DIF
[5 empty] | Progress payment waiver & release (Civ Code 3262) | DIF
[5 empty] | Claims and dispute resolution (PCC 20104) | DIF
[5 empty] | Anti-trust claim assignment (PCC 7103.5) | DIF
[5 empty] | Stormwater Language (PCC 28026) | DIF
[5 empty] | DIR registration (Labor Code 1771.1(a)) (As of 1/1/2015) | DIF
[5 empty] | Require all contractors, subcontractors, and vendors to pay at least General Prevailing Wage Rates to all workers | DIF
[5 empty] | Require all contractors, subcontractors, vendors, equipment operators and owner operators engaged to perform work on a Segment to submit certified weekly payroll records to the Developer for inspection by the City | DIF
[5 empty] | Require all contractors, subcontractors, and vendors to comply with the provisions that the contractor shall not discriminate in its employment practices against any employee, or applicant for employment, because of such person’s race, religion, national origin, ancestry, sex, sexual orientation, age, physical handicap, marital status or medical condition. | DIF
| N | 16 | 3.3 | Developer written statement and pictures verifying the General Prevailing Wage Rates were posted at the job-site in a conspicuous place and available to all employees and applicants for employment |  | Engineering
| O | 18 | 3.5, 4.2 | Permits - Developer to list in the space below all the permits required | All permits required by the City or any other government agency affected by the construction of the Improvements (Land Use Entitlement, Encroachment) | Engineering
[5 empty] | Invoice supporting permit fees required | Engineering
[5 empty] | Warrants supporting permit fees paid | Engineering
| P | 3 | 2.2, 3.1 | "As-built" or recorded drawings or plans for the Improvement | Certified and reflecting the condition of the Improvement as constructed in accordance with the Conditions of Approval (COA) | Engineering
| Q | 3 | 3.5 | Acceptance letter from City Engineering Dept |  | Engineering
| R | 3 | 2.2, 3.5 | Copy of NOC filed with San Bernardino County | Filing is within 10-days after receiving notification that the segment was constructed in accordance with the Plans, pursuant to the provisions of Section 3093 of the California Civil Code. | Engineering
| S | 3 | 2.2 | Copy of mechanic's lien | All final releases or documentation that there are no outstanding claims or liens from all contractors, subcontractors, and vendors that received payment as part of the Eligible or Actual Costs or Reimbursement | Engineering
[5 empty] | Guaranteeing that no such claims of liens will be recorded or become a lien upon any of the real property required for the Improvement | Engineering
| T | 3, 4 | 2.2 | Acceptable title | The City Engineer shall review and approve the title report unless it reveals a matter which could materially affect the City’s or its designee’s use and enjoyment of any part of the property or easement covered by the title report. | Engineering
| U | 5 | 3.6 | Maintenance bond (only for subdivision) | Term is one year from the Acceptance Date | Engineering
| V | 3 |  | Binder cover letter from Developer notifying the City Engineer that the construction of a DIF Program Segment has been completed in accordance with the plans and specifications |  | Engineering
| W | 9, Exhibit 6 |  | Form of DIF Credit Request |  | DIF
| X | 6, Exhibit 5 |  | Form of Certificate of Regional or Local Adjacent DIF Credit |  | DIF
| Y | 9, Attachment 1 |  | Summary of Improvements and Requested DIF Credits form |  | DIF
| Z | 10, Exhibit 7 |  | Form of Certificate of DIF Reimbursement |  | DIF
| AA | 6 |  | DIF Credit Facilities - Summary of DIF Program and Eligible Costs form | Developer identified DIF Credit infrastructure category | Engineer/DIF
[5 empty] | Developer identified whether the DIF Credit is Regional or Local Adjacent DIF Program Improvement | Engineer/DIF
| AB | 7, 8, 12.1, 12.2, 12.3, 12.4 |  | DIF Credit Facilities - Summary of Expended and Eligible Costs form | DIF Credit issued by City shall be limited to the amount of the DIF Program Costs for the Improvement accepted | Engineer/DIF
[5 empty] | DIF Program Costs for the Improvements accepted shall be those in effect at the time the Improvement is Completed and accepted by the City | Engineer/DIF
[5 empty] | Total amount of DIF Credit to be issued to Developer for completion of all Improvements shall be limited to the respective DIF Infrastructure Category | Engineer/DIF
[5 empty] | 10% of the DIF Program Costs, for those design costs portion of the Improvements shall be issued to NMC Builders LLC | Engineer/DIF
[5 empty] | Reimbursement amount does not include interest cost | Engineer/DIF
[5 empty] | Reimbursement amount is not for DIF payments made by development that does not benefit from Developer's construction DIF Program Improvements or from DIF payments received for other DIF categories | Engineer/DIF
[5 empty] | In the Regional DIF category of Sewer Collection Facilities, no DIF Reimbursement shall be available from DIF payments until the City's obligations to repay IEUA have been met | Engineer/DIF
[5 empty] | Reimburse in order of the date of certificate issuance | Engineer/DIF
| AC | 9 |  | Change orders |  | Engineer
| AD | 9 |  | Invoices supporting items on the DIF Credit Facilities - Summary of Expended and Eligible Costs form - Invoices need to be detailed to show each item. Not lump sum. Traceable from form to invoice. |  | Engineer/DIF
| AE | 9 |  | Warrants supporting items on the DIF Credit Facilities - Summary of Expended and Eligible Costs form - Traceable from form to warrant. |  | Engineer/DIF
| AF |  | 1.1, 2.4 | Developer certificate contain an original or specimen signature of each person designated as Developer Representative |  | Engineer/DIF

## Construction Certification
Facilities Construction Certification
I hereby certify under penalty of perjury under the laws of the State of California that all of the improvements were constructed in compliance with California Labor code, California Government Code, California Public Contracts Code and all of the representations made herein are true and correct for the following facilities/segments:
Signature:
Name:
Title:
Date:

## Summary Actual & Eligible Costs
Summary of Actual Expended and Eligible Costs
DIF Actual Costs
DIF Category | DIF Program Project No. | DIF Program Project Description | Segment Description | Total DIF Program Costs per Segment | Maximum DIF Program Funded Costs (From DIF Program)

## DIF Expend Eligible Costs
DIF Credit Facilities - Expended and Eligible Costs
DIF Program Project No. and Description:
Total DIF Program Cost:
Total NMC Builder Design Cost:
Maximum Expended & Eligible Cost: |  | 0
List all Contractors, Suppliers, and Vendors
(Section i) Construction Cost (see Eligible Cost definition in agreement) |  |  | Final Actual Amount Paid
List all Construction Contracts by Name of Contractor/License No.
1.
2.
3.
4.
|  | Construction Sub-Total | 0
(Section ii) Construction Related Costs (see Eligible Cost definition in agreement) |  |  | Final Actual Amount Paid
Provide Name of Contractor and Describe Work Performed
1.
2.
3.
4.
|  | Construction Related Sub-Total | 0
(Section iii) Real Property Costs (see Eligible Cost definition in agreement) |  |  | Final Actual Amount Paid
Provide Name of Contractor and Describe Work Performed
1.
2.
3.
|  | Real Property Sub-Total | 0
(Section iv) Bid Document Costs (see Eligible Cost definition in agreement) |  |  | Final Actual Amount Paid
Provide Name of Contractor and Describe Work Performed
1.
2.
3.
|  | Bid Document Sub-Total | 0
(Section v) Fees Costs (see Eligible Cost definition in agreement) |  |  | Final Actual Amount Paid
Provide Name of Agency and Type of Fee or Permit
1.
2.
3.
|  | Fees Sub-Total | 0
(Section vi) Construction Management Costs (see Eligible Cost definition in agreement) |  |  | Final Actual Amount Paid
Describe Construction Management Services - List all Service Providers and Amounts
1.
2.
3.
4.
|  | Construction Management Sub-Total | 0
(Section vii) Professional Services Costs (see Eligible Cost definition in agreement) |  |  | Final Actual Amount Paid
Provide Name of Contractor and Type of Work Performed
1. | NMC Builders design cost, if applicable
2.
3.
|  | Professional Services Sub-Total | 0
|  | Actual Cost Grand Total | 0
|  | 5% Construction Management Limitation Amount | 0
|  | 15% Design & Construction Management Limitation Amount | 0
|  | Total Expended and Eligible Costs | 0

## CFD Acual Cost Definition
Actual Cost Definition
“Actual Cost” means, with respect to a Segment, an amount equal to the sum of (a) the Developer’s actual, reasonable cost of constructing such Segment (including grading for such construction), including labor, material and equipment costs, (b) the Developer’s actual, reasonable cost of designing and preparing the Plans for such Segment, including engineering services provided in connection with designing and preparing such Plans, (c) the Developer’s actual, reasonable cost of any performance and maintenance bonds and insurance, including title insurance, required hereby for such Segment, (d) the Developer’s actual, reasonable cost of any real property or interest therein, other than any such real property or interest therein to be conveyed with a Circulation System Segment, which real property or interest therein is either necessary for the construction of such Segment (e.g., temporary construction easements, haul roads, etc.) or is required to be conveyed with such Segment in order to convey Acceptable Title thereto to the City or its designee, (e) the Developer’s actual, reasonable cost of environmental evaluations required in the City’s reasonable determination specifically for such Segment, (f) the amount of any fees actually paid by the Developer to governmental agencies in order to obtain permits, licenses or other necessary governmental approvals and reviews for such Segment, including the City plan check, processing and inspection fees for such Segment, (g) the Developer’s actual, reasonable cost for construction management services for such Segment, which cost shall not exceed 5% of the cost of constructing such Segment, as determined pursuant to clause (a) of this definition, and (h) the Developer’s actual, reasonable cost for professional services directly related to the construction of such Segment, including engineering, inspection, construction staking, materials testing and similar professional services, all as specified in a Payment Request that has been reviewed and approved by the City Engineer; provided, however, that (i) no item of cost relating to a Segment shall be included in more than one category of cost specified in clauses (a) through (h) of this definition, (ii) except with respect to items of cost for construction management services specified in clause (g) that are provided by the Developer or an Affiliate thereof rather than a third party, each item of cost shall include only amounts actually paid by the Developer to third parties, other than Affiliates of the Developer, and shall not include overhead or other internal expenses of the Developer, and (iii) the aggregate cost of items specified in clauses (e) through (h) shall not exceed 15% of the cost of constructing such Segment, as determined pursuant to clause (a) of this definition.

## CFD Expended Eligible Costs
CFD Segments - Expended and Eligible Costs
CFD Segment No. and Description:
Total CFD Segment Cost:
Total NMC Builder Design Cost:
Maximum Expended & Eligible Cost: |  | 0
List all Contractors, Suppliers, and Vendors
(Section a) Costs of Construction (see Actual Cost definition in agreement) |  |  | Final Actual Amount Paid
List all Construction Contracts by Name of Contractor/License No.
1.
2.
3.
4.
|  | Cost of Construction Sub-Total | 0
(Section b) Preparation of Plans and Engineering Services (see Actual Cost definition in agreement) |  |  | Final Actual Amount Paid
Provide Name of Service Provider and Describe Work Performed
1. | NMC Builders design cost, if applicable
2.
3.
4.
|  | Preparations of Plans and Engineering Services Sub-Total | 0
(Section c) Performance and Maintenance Bonds (see Actual Cost definition in agreement) |  |  | Final Actual Amount Paid
Provide Name of Service Provider and Bond
1.
2.
3.
|  | Performance and Maintenance Bonds Sub-Total | 0
(Section d) Real Property Costs (see Actual Cost definition in agreement) |  |  | Final Actual Amount Paid
Provide Name of Contractor and Describe Work Performed
1.
2.
3.
|  | Real Property Sub-Total | 0
(Section e) Environmental Evaluations (see Actual Cost definition in agreement) |  |  | Final Actual Amount Paid
Provide Name of Service Provider and Describe Service
1.
2.
3.
|  | Environmental Evaluations Sub-Total | 0
(Section f) Governmental Fees (see Actual Cost definition in agreement) |  |  | Final Actual Amount Paid
Provide Name of Agency and Type of Fee or Permit
1.
2.
3.
|  | Governmental Fees Sub-Total | 0
(Section g) Construction Management (see Actual Cost definition in agreement) |  |  | Final Actual Amount Paid
Describe Construction Management Services - List all Service Providers and Amounts
1.
2.
3.
|  | Construction Management Sub-Total | 0
(Section h) Other Professional Services (see Actual Cost definition in agreement) |  |  | Final Actual Amount Paid
Describe all other Professional services, including engineering, inspection, construction staking, materials testing and similar professional services
1.
2.
3.
|  | Other Professional Services Sub-Total | 0
|  | Actual Cost Grand Total | 0
|  | 5% Construction Management Limitation Amount | 0
|  | 15% Design & Construction Management Limitation Amount | 0
|  | Total Expended and Eligible Costs | 0

## Credit Amount Calc
CFD # _____ CREDIT AMOUNT CALCULATION*
(Acquisition Agreement Section 2.4)
Segment No. | Program Budget | Acutal Costs | (Under) Program Costs | Over Program Costs
Totals | 0 | 0 | 0 | 0
Eligible Credit Amount =
* Fifty percent (50%) of the proceeds allocated at bond issuance to Tier-1 facilities must be expended prior to submitting a Credit request for review.